## Project
Task | Start date | End Date | Category | Category2 | Progress | Days | Person
Project kick-off and stakeholder alignment | 2026-10-12 | 2026-10-12 | Project Delivery | Discovery | 100% | 0 | Adam
Requirements workshop 1: business goals and decisions | 2026-10-13 | 2026-10-13 | Project Delivery | Discovery | 100% | 0 | Adam
Requirements workshop 2: KPIs, dimensions and filters | 2026-10-14 | 2026-10-14 | Project Delivery | Discovery | 100% | 0 | Adam
Identify report users and access requirements | 2026-10-14 | 2026-10-15 | Project Delivery | Discovery | 100% | 1 | Adam
Document current reporting process and pain points | 2026-10-15 | 2026-10-16 | Project Delivery | Discovery | 100% | 1 | Adam
Create and prioritize product backlog | 2026-10-16 | 2026-10-19 | Project Delivery | Planning | 90% | 3 | Adam
Define MVP scope and acceptance criteria | 2026-10-19 | 2026-10-20 | Project Delivery | Planning | 50% | 1 | Adam
Confirm data owners and source systems | 2026-10-20 | 2026-10-21 | Solutions Delivery | Data | 25% | 1 | Adam
Data profiling and completeness checks | 2026-10-21 | 2026-10-23 | Solutions Delivery | Data | 25% | 2 | Stefa
Validate KPI definitions and calculation rules | 2026-10-22 | 2026-10-26 | Solutions Delivery | Data | 25% | 4 | Stefa
Prepare navigation and page wireframes | 2026-10-22 | 2026-10-26 | Solutions Delivery | UX / Design | 10% | 4 | Stefa
Wireframe review with key users | 2026-10-27 | 2026-10-27 | Solutions Delivery | UX / Design | 10% | 0 | Stefa
Sprint 1 planning | 2026-10-28 | 2026-10-28 | Solutions Delivery | Sprint 1 | 0% | 0 | Stefa
Build data ingestion and Power Query transformations | 2026-10-28 | 2026-11-03 | Solutions Delivery | Sprint 1 | 0% | 6 | Stefa
Build initial semantic model and relationships | 2026-10-29 | 2026-11-04 | Solutions Delivery | Sprint 1 | 0% | 6 | Stefa
Create core DAX measures for MVP | 2026-11-02 | 2026-11-06 | Solutions Delivery | Sprint 1 | 0% | 4 | Stefa
Sprint 1 demo and feedback session | 2026-11-09 | 2026-11-09 | Solutions Delivery | Sprint 1 | 0% | 0 | Stefa
Refine backlog after Sprint 1 review | 2026-11-09 | 2026-11-10 | Project Delivery | Planning | 0% | 1 | Stefa
Sprint 2 planning | 2026-11-11 | 2026-11-11 | Solutions Delivery | Sprint 2 | 0% | 0 | Adam
Build MVP report pages and interactions | 2026-11-11 | 2026-11-19 | Solutions Delivery | Sprint 2 | 0% | 8 | Adam
Configure drill-through, tooltips and navigation | 2026-11-16 | 2026-11-20 | Solutions Delivery | Sprint 2 | 0% | 4 | Adam
Implement row-level security design | 2026-11-17 | 2026-11-20 | Solutions Delivery | Security | 0% | 3 | Adam
Sprint 2 demo and feedback session | 2026-11-23 | 2026-11-23 | Solutions Delivery | Sprint 2 | 0% | 0 | Adam
Sprint 3 planning | 2026-11-24 | 2026-11-24 | Solutions Delivery | Sprint 3 | 0% | 0 | Clark
Apply feedback and finalize report UX | 2026-11-24 | 2026-11-30 | Solutions Delivery | Sprint 3 | 0% | 6 | Clark
Reconcile report totals with source data | 2026-11-25 | 2026-12-01 | Quality Assurance | Testing | 0% | 6 | Clark
Performance optimization and model cleanup | 2026-11-27 | 2026-12-02 | Quality Assurance | Testing | 0% | 5 | Clark
Prepare UAT scenarios and test cases | 2026-11-30 | 2026-12-02 | Quality Assurance | Testing | 0% | 2 | Clark
User acceptance testing | 2026-12-03 | 2026-12-07 | Quality Assurance | Testing | 0% | 4 | Adam
Resolve UAT findings | 2026-12-04 | 2026-12-09 | Solutions Delivery | Sprint 3 | 0% | 5 | Adam
Final business approval | 2026-12-10 | 2026-12-10 | Release Management | Approval | 0% | 0 | Adam
Publish report to Power BI workspace | 2026-12-11 | 2026-12-11 | Release Management | Deployment | 0% | 0 | Stefa
Configure refresh, permissions and distribution | 2026-12-11 | 2026-12-14 | Release Management | Deployment | 0% | 3 | Stefa
Create user guide and release notes | 2026-12-09 | 2026-12-14 | Release Management | Documentation | 0% | 5 | Stefa
Training and report handover | 2026-12-15 | 2026-12-15 | Release Management | Handover | 0% | 0 | Stefa
Hypercare and adoption feedback | 2026-12-16 | 2027-01-01 | Release Management | Hypercare | 0% | 16 | Stefa
Close project and capture lessons learned | 2027-01-04 | 2027-01-04 | Project Delivery | Closure | 0% | 0 | Stefa